HORQUVA · OBA CORE

Executive Agent Interface

Implementation Plan — Workstream W-L

Version 1.0  ·  27 August 2026  ·  For team execution

Companion document: 2026-08-27-w-l-agent-interface-design.md

Contents

If the list below is empty, select it and press F9 (Windows) or right-click → Update Field to build it.

# OBA Core — Executive Agent Interface

## Implementation Plan (Workstream W-L)

Document control

| Field | Value |
| --- | --- |
| Version | 1.0 |
| Date | 2026-08-27 |
| Status | For team execution — pending sign-off on §4.2 |
| Workstream | W-L |
| Branch | ocos/develop |
| Companion document | docs/superpowers/specs/2026-08-27-w-l-agent-interface-design.md (architecture and rationale) |
| Audience | Backend, frontend and data engineers implementing the agent layer |
| Prior art | Decisions D-01 … D-68; workstreams W-A … W-K, all closed |

How the two documents relate. The design document answers why and what: why the agent runs in-process, why there are thirteen tools rather than a hundred and fifty, why grounding needs five layers. This document answers how, in what order, and how we know it is done. If the two ever disagree, the design document wins on intent and this one wins on sequence.

# 1. Purpose and how to use this document

This is the build plan for an executive-facing conversational agent over OBA Core. It is written to be executed by more than one engineer working in parallel, so every task states its lane, its dependencies, its interface contract, and the condition under which it is finished.

Read sections 1 through 9 before writing any code. They contain the invariants that the rest of the plan assumes. A task executed correctly in isolation but in violation of §6.4 will have to be redone.

Task format. Every task in sections 10 through 13 uses the same block:

- Lane — which engineer can pick it up (Backend, Frontend, Data, or Any)

- Depends on — tasks that must be complete first

- Estimate — engineer-days, assuming familiarity with the codebase

- Why — the reason this task exists, so it can be challenged rather than followed blindly

- Files — what gets created or changed

- Contract — the interface other tasks will code against, written out in full

- Steps — the implementation sequence

- Tests — what proves it works

- Done when — the acceptance condition

A note on code in this plan. Prior workstreams in this repository wrote out every line of implementation code in the plan itself. That suited a single agent executing mechanically. This plan is for a team, so it writes out contracts, schemas, protocols and acceptance criteria in full — the things two engineers must agree on to work in parallel — and describes implementation precisely without dictating every line. Where a decision is genuinely load-bearing (SQL schema, SSE event protocol, tool envelope, provider interface) the code is complete and normative.

# 2. Scope

## 2.1 In scope

A conversational interface, available on every page of the workspace, that:

- Answers natural-language questions about the organization using the MVP's existing computed

intelligence, at executive depth rather than in one-line templates.

- Explains what a metric means, how it was computed, and whether it is measured or authored.

- Runs the MVP's existing what-if simulations on demand and reasons over the real results.

- Runs a new succession simulation (reassigning one person's responsibilities to another).

- Offers — never forces — navigation to the page and section where a finding lives, and explains what

the user is looking at when they arrive.

- Sustains multi-turn follow-up reasoning over prior results.

- Refuses to invent numbers, entities, or metric definitions, with mechanical enforcement rather than

prompt-based hope.

## 2.2 Out of scope

Stated explicitly so nobody builds them by accident:

- Any write to organizational data. All thirteen tools are reads or pure computations. D-04

deferred the write loop for the whole product; the agent is not an exception to it.

- Multi-tenancy. D-01 fixed the product as single-tenant. Conversations are scoped per user for

privacy and audit, not for tenant isolation.

- Voice input/output. The existing /api/voice naming is historical. This is text.

- Model fine-tuning, embeddings, or a vector store. See design document §5.3.

- Replacing the existing dashboard. The agent sits alongside the pages, not instead of them.

- Agent-initiated actions or notifications. The agent responds; it does not act or schedule.

## 2.3 Success criteria — the acceptance demo

W-L is complete when the following session runs end to end against live data, in the browser, with the validator reporting clean on every turn:

| # | User says | The system must |
| --- | --- | --- |
| 1 | "What's our biggest organizational risk right now?" | Call the intelligence tools, name a real entity, quote its real predicted score and reasons, and explain why it matters in executive terms. |
| 2 | "What happens if Sarah leaves?" | Resolve "Sarah" to Sarah Mitchell, run the real employeeLeaves simulation, report the real impacted agents, workflows, severity and health delta. |
| 3 | "Which workflows are affected?" | Answer from the previous turn's result without re-running, and list only workflows that appeared in it. |
| 4 | "Why is that one the biggest concern?" | Pull the workflow's real profile — criticality, documentation state, owner, dependencies — and reason from it. |
| 5 | "What if Omar Hassan takes over her responsibilities?" | Run the new reassignment simulation, and report the residual risk that remains after the transfer. |
| 6 | "Show me where this is in the app." | Offer a valid navigation target; on click, land on the right page with the right block highlighted, with the explanation still on screen. |

Plus: every number in every answer traces to a tool result; no invented entity names; the tool trace is visible; and a question whose data is genuinely missing produces an honest "not measured" rather than an estimate.

# 3. Provider selection: Google Gemini free tier

## 3.1 The decision

Provider: Google Gemini API, free tier. Model: `gemini-3.7-flash`. SDK: `@google/genai`.

This satisfies the requirement to build and run the agent at zero cost. The provider is reached through an adapter interface (§8.4), so switching later is a configuration change and one new file, not a rewrite.

## 3.2 Why Gemini and not the alternatives

| Option | Verdict | Reasoning |
| --- | --- | --- |
| Gemini free tier | Selected | Function calling, 1M context, and streaming are all included on the free tier. Flash-tier token-per-minute headroom comfortably absorbs our ~10k-token prefix plus tool results. No credit card required. |
| Groq free tier | Rejected | The free tier caps at roughly 6,000 tokens per minute. Our system prompt, tool definitions and organization roster alone are approximately 9,300 tokens. A single turn would exceed the entire per-minute budget before the user's question is even added. Architecturally incompatible, not merely tight. |
| Local model via Ollama | Rejected for v1, viable later | Free forever and fully private, but multi-step tool chaining is where small models fail, and our acceptance demo is a four-turn chain. Worth revisiting as a fallback provider once the adapter exists and the golden-question suite (§18.2) can measure the quality drop objectively. |
| Anthropic Claude | Deferred, not discarded | Higher answer quality, at roughly $0.05 per turn. The adapter keeps this a one-line switch. Recommended for customer-facing demos; see §20.4. |

## 3.3 What the free tier changes about the architecture

Four consequences that engineers must know, because they differ from the companion design document, which was written provider-neutrally with Anthropic as its reference:

1. Requests-per-day becomes the binding constraint, not money. Free-tier Flash allows on the order of 1,500 requests per day per project, and one agent turn costs several requests — one for the initial call plus one per tool round trip. At a cap of eight tool iterations, a worst-case turn is nine requests. Budget on the order of 150–400 turns per day across the entire project, shared by every developer and every demo. This is why §10.7 puts the provider behind a per-user turn budget from day one, and why §20.2 makes quota a monitored operational metric rather than an afterthought.

2. There is no prompt-cache prefix to protect, so volatile context can go in the system instruction. The companion design routed per-turn context through a mid-conversation system message specifically to avoid invalidating a cached prefix. Gemini's systemInstruction is sent per request anyway, so that constraint disappears: the turn's snapshot timestamp, graph load time, current page and any validator repair instruction all go straight into systemInstruction. This is simpler and it keeps operator instructions out of the user turn, which preserves the injection-safety property that motivated the original design.

3. Tool input validation is our responsibility. Gemini supports only a subset of the OpenAPI schema and offers no equivalent of a strict-mode guarantee that arguments will conform. Schemas must therefore be kept flat and modest, and every tool must validate its own input before executing (§11.1). This is a real task, not a defensive nicety — it was previously free.

4. Model identifiers move. Gemini model IDs are versioned and rotate faster than this document will be revised. The model ID must live in an environment variable and never be hardcoded, and the team must confirm the current free-tier model row in AI Studio on the day they start (§7.1).

## 3.4 What does not change

Everything that carries the product's integrity is provider-independent: the thirteen tools, the frozen roots invariant, the tool result envelope, the numeric citation validator, the entity allowlist, the metric glossary, the navigation catalog, the SSE protocol, and the conversation schema. A weaker model degrades prose quality and multi-step chaining; it does not degrade correctness, because correctness is enforced outside the model.

# 4. Assumptions and open decisions

## 4.1 Assumptions this plan makes

The plan is written to be executable now rather than blocked. Where a decision is open, the recommendation from the design document has been assumed and the affected tasks are marked.

| ID | Assumption taken | Tasks affected if reversed |
| --- | --- | --- |
| D-69 | First shippable slice is Phases 1–2: grounded Q&A, no navigation, no succession. | Sequencing only. |
| D-70 | On reassignment: the successor inherits assets, but not backup coverage and not documentation state; the successor's existing load counts against them. | 13.1, 13.2 |
| D-71 | Navigation catalog is shared via a single JSON file if the Vercel build can resolve it; otherwise duplicated with a CI drift test. | 12.2 |
| D-72 | voice.js and executive.js are retained as a non-LLM fallback when the agent is disabled, not deleted. | 11.6, 13.5 |
| D-73 | Numeric validator performs one automatic repair round, then annotates and logs. | 11.8 |
| D-74 | Provider is Gemini free tier, behind an adapter. | 10.7 |
| D-75 | Render free plan for now; paid tier before any customer-facing demo. | 19.2 |
| D-76 | Provider adapter is mandatory, not optional. | 10.7 |

## 4.2 Sign-off required before Phase 1 starts

D-70 is the only genuinely blocking item. Tasks 13.1 and 13.2 cannot be written without it, and they are the flagship capability. Everything else can proceed under the assumption above and be revisited cheaply.

# 5. Team, lanes and sequencing

## 5.1 Lanes

| Lane | Owns | Can start |
| --- | --- | --- |
| Data | Migration, schema, seed verification | Immediately |
| Backend | Domain modules, tools, provider adapter, agent loop, SSE route, validators | Immediately |
| Frontend | Navigation extraction, agent client, panel components | After 12.1, which has no backend dependency |

## 5.2 Critical path

10.2 (roots split)  →  10.6 (turn context)  →  11.1 (tool registry)  →  11.2 (read tools)

→  11.5 (agent loop)  →  11.6 (SSE route)  →  12.3 (agent client)  →  12.5 (panel)

Everything else hangs off this spine. The two longest single tasks are 11.5 (the agent loop) and 13.1 (the reassignment simulation).

## 5.3 What can run in parallel from day one

- Data: 10.5 (migration) depends on nothing.

- Backend A: 10.2 → 10.6 → 11.1 → 11.2 (the spine).

- Backend B: 10.3 (resolver) and 10.4 (glossary) are self-contained pure modules with no

dependencies beyond the roots bundle shape.

- Frontend: 12.1 (navigation extraction) touches only existing frontend code and can be merged

before any agent code exists.

## 5.4 Estimate summary

| Phase | Tasks | Engineer-days |
| --- | --- | --- |
| Phase 1 — Foundation | 7 | 7 |
| Phase 2 — The agent turn | 9 | 13 |
| Phase 3 — Frontend and navigation | 7 | 9 |
| Phase 4 — Succession and hardening | 5 | 7 |
| Total | 28 | 36 |

With three engineers in the lanes above, expect roughly three calendar weeks. These estimates assume familiarity with this codebase; add 30 percent for an engineer new to it, and read §6 first regardless.

# 6. Engineering standards for this workstream

## 6.1 Branching and commits

- Work on ocos/develop, the branch every prior workstream landed on.

- One task per commit. Never batch. This is the convention that made W-C through W-K auditable.

- Commit messages name the task: feat(W-L 11.2): read tools over the frozen roots bundle.

- Where a task closes a decision, name it: fix(D-70): reassignment does not transfer backup coverage.

## 6.2 A warning specific to this repository

`git add <file>` is not safe here without checking first. Several files historically carry pre-existing uncommitted work unrelated to any workstream. Run git status --short at the start of every session and git diff <file> before staging anything that was already modified. If a file's diff is larger than your own edit, commit the unrelated work separately first, naming it as pre-existing, then make your change on top. This has bitten previous workstreams.

## 6.3 Definition of done

A task is done when all of the following hold:

- The tests named in the task pass.

- node tests/run-all.js passes in full from backend/.

- For frontend tasks, tsc --noEmit is clean from frontend/.

- For anything observable only over HTTP, it has been verified against a restarted local server —

Node does not hot-reload, and a stale process silently serves the old code. This caught two false    completions during W-D.

- For anything visual, it has been verified in a real browser, not merely typechecked.

- The commit is made and names the task.

## 6.4 Non-negotiable invariants

Violating any of these produces work that must be redone. They are the reason the product is trustworthy.

I-1 — One roots read per turn. Every tool in a single turn reads the same frozen bundle. No tool issues its own database query. If a tool needs data not in the bundle, the bundle gains a field; the tool does not gain a query.

I-2 — No tool writes. Reads and pure computations only. No inserts, updates, or deletes to any organizational table. Conversation and usage tables are the sole exception and are written by the route, never by a tool.

I-3 — The model never computes an organizational metric. If an answer needs a number, a tool returns it. If a comparison is needed, a tool computes the comparison. There is no arithmetic in the model's output path.

I-4 — Definitions come from `definitions.js`. Criticality, thresholds, SPOF status and evidence gating are never reimplemented inside a tool. atOrAbove() and spofVerdict() are the only authorities.

I-5 — Provenance survives to the client. Every tool result carries its computation timestamp, source and inputs. Routes and components pass it through rather than stripping it.

I-6 — Insufficient evidence is a result, not an error. When an evidence gate reports insufficient coverage, that is reported honestly. It is never rounded into a number or silently omitted.

I-7 — All provider access goes through the adapter. No file outside backend/agent/providers/ imports a vendor SDK.

# 7. Prerequisites and environment setup

## 7.1 Accounts and credentials

| Item | How | Owner |
| --- | --- | --- |
| Google AI Studio API key | Create a project at aistudio.google.com and generate an API key. No credit card required for the free tier. | Tech lead |
| Confirm the current free-tier model row | In AI Studio, check which Flash model currently carries a free-tier row and note its exact ID and its RPM / TPM / RPD limits. Model IDs rotate. Record the values in §17.2 of this document. | Tech lead, day 1 |
| Render dashboard access | To set backend environment variables. | Tech lead |
| Supabase access | To run the migration. | Data lane |

Do not commit the API key. It goes in backend/.env locally and the Render dashboard in production, following the existing pattern for SUPABASE_KEY and JWT_SECRET.

## 7.2 Local development

Both servers run from .claude/launch.json, which already defines backend (port 3000) and frontend (port 3001), both with autoPort enabled.

- Do not assume ports 3000 and 3001 are free. Another session commonly holds them. Let autoPort

pick, then point frontend/.env.local's NEXT_PUBLIC_API_URL at whatever port the backend actually   took, and restart the frontend for the change to take effect.

- frontend/.env.local is gitignored local configuration. Retarget it freely; never commit it.

- Log in through the real UI using the ADMIN_EMAIL / ADMIN_PASSWORD values already present in

backend/.env. There is no need to invent test credentials.

## 7.3 New dependency

One package, backend only:

cd backend && npm install @google/genai

Node 22 or later is already required by backend/package.json and by Render.

## 7.4 Environment variables

New variables introduced by this workstream. Full reference in Appendix C.

| Variable | Where | Default | Purpose |
| --- | --- | --- | --- |
| AGENT_ENABLED | backend/.env, Render | false | Master feature flag. When false the agent routes are not mounted at all. |
| AGENT_PROVIDER | backend/.env, Render | gemini | Selects the adapter. gemini or anthropic. |
| AGENT_MODEL | backend/.env, Render | gemini-3.7-flash | Model ID. Never hardcode this in source. |
| GEMINI_API_KEY | backend/.env, Render (sync: false) | — | Provider credential. |
| ANTHROPIC_API_KEY | backend/.env, Render (sync: false) | — | Only if AGENT_PROVIDER=anthropic. |
| AGENT_MAX_ITERATIONS | backend/.env | 8 | Hard cap on tool rounds per turn. |
| AGENT_TURN_TIMEOUT_MS | backend/.env | 120000 | Wall-clock cap per turn. |
| AGENT_DAILY_TURN_BUDGET | backend/.env | 40 | Per-user turns per day. Sized against the provider's request-per-day quota. |
| NEXT_PUBLIC_AGENT_ENABLED | frontend/.env.local, Vercel | false | Hides the agent UI when the backend has it disabled. |

# 8. Architecture summary

Full rationale is in the companion design document. This section is the working reference.

## 8.1 Component map

| Layer | Component | Responsibility |
| --- | --- | --- |
| Route | routes/agent/chat.js | Auth, rate limit, budget, SSE lifecycle |
| Orchestration | agent/loop.js | The tool-calling loop, iteration cap, abort |
| Provider | agent/providers/*.js | The only vendor-specific code |
| Tools | agent/tools/*.js | Thirteen tools over the frozen bundle |
| Context | agent/turnContext.js | One roots read, one intelligence computation, one graph snapshot |
| Guards | agent/validators.js | Numeric citation and entity allowlist checks |
| Truth | domain/* | Unchanged, except one refactor and one new simulation |
| Persistence | four new tables | Conversations, messages, tool calls, usage |

## 8.2 The turn lifecycle

POST /api/agent/chat                    Accept: text/event-stream

body: { conversationId?, message, pageContext? }

|

+-- requireAuth                       existing middleware, unchanged

+-- rateLimit(keyFn: req.user.sub)    existing middleware, new key function

+-- daily turn budget check           429 when exhausted

|

+-- load conversation history         agent_conversations + agent_messages

+-- BUILD TURN CONTEXT ------------------------------------------

|     roots      = await derived.loadRoots(supabase)     ONE read

|     intel      = derived.computeAllFromRoots(roots)    pure

|     graph      = domain.graph.source()                 snapshot metadata

|     snapshotAt = new Date().toISOString()

|     tools      = buildTools(turnContext)               closures capture the bundle

|

+-- SSE open, emit `ready` immediately

|

+-- loop, max AGENT_MAX_ITERATIONS:

|     provider.stream({ systemInstruction, history, tools })

|       text delta        -> SSE `token`

|       tool call         -> SSE `tool_start`, validate input, execute,

|                            SSE `tool_done`, append result

|       no tool call      -> break

|

+-- validators: numeric citation (one repair round), entity allowlist

+-- persist: message, tool trace, usage, validator verdict

+-- SSE `done` { navigationOffer?, toolTrace[], provenance, usage }

## 8.3 File layout

backend/

routes/agent/

index.js            router assembly, mount guard

chat.js             the SSE endpoint

agent/

loop.js             the tool-calling loop

turnContext.js      frozen bundle construction

constitution.js     system instruction text and roster builder

validators.js       numeric + entity guards

registry.js         tool assembly and input validation

tools/

resolve.js  read.js  intelligence.js  simulate.js  navigate.js

providers/

index.js          adapter selection

gemini.js         @google/genai implementation

anthropic.js      reference implementation, added in Phase 4

domain/

resolve.js          NEW  entity resolution

metricGlossary.js   NEW  metric definitions as data

navigationCatalog.js NEW navigation targets, validated

pageContext.js      NEW  page section values

derived.js          MODIFIED  computeAllFromRoots split

simulations.js      MODIFIED  employeeLeavesWithSuccessor

sql/

15_agent_layer.sql  NEW

frontend/

lib/

navigate.ts         NEW  extracted single navigation path

agentClient.ts      NEW  SSE reader

components/agent/

AgentProvider.tsx  AgentPanel.tsx  AgentMessage.tsx

AgentComposer.tsx  ToolTrace.tsx   NavigationOffer.tsx

## 8.4 The provider adapter

Every provider implements this interface. Nothing outside providers/ may import a vendor SDK (I-7).

/**

* @typedef {Object} ProviderTool

* @property {string} name

* @property {string} description

* @property {Object} parameters      JSON-Schema subset: object, flat properties, enums

*

* @typedef {Object} ProviderTurn

* @property {string} systemInstruction

* @property {Array<{role: 'user'|'model', parts: Array}>} history

* @property {ProviderTool[]} tools

* @property {AbortSignal} signal

*

* @typedef {Object} ProviderEvent

*   { type: 'text',      text: string }

*   { type: 'tool_call', id: string, name: string, args: object }

*   { type: 'done',      usage: { inputTokens, outputTokens }, finishReason: string }

*   { type: 'error',     error: Error, retryable: boolean }

*/

module.exports = {

/** Async generator yielding ProviderEvent. */

async *stream(turn) {},

/** Append a tool result to history in this provider's wire shape. */

appendToolResult(history, { id, name, result }) {},

/** Append the model's own turn to history. */

appendModelTurn(history, parts) {},

/** Provider identity for logging and usage rows. */

describe() { return { provider: 'gemini', model: process.env.AGENT_MODEL } },

}

The loop in agent/loop.js knows only this interface. Swapping provider is then a new file plus an environment variable.

# 9. Data layer and migration

## 9.1 Migration file

backend/sql/15_agent_layer.sql, following the existing numbered migration convention.

-- W-L: agent conversation, audit and usage tables.

-- These are the ONLY tables the agent layer writes to. No organizational

-- table is written by any agent code path (invariant I-2, decision D-04).

CREATE TABLE IF NOT EXISTS agent_conversations (

id              uuid PRIMARY KEY DEFAULT gen_random_uuid(),

user_id         text        NOT NULL,

title           text,

created_at      timestamptz NOT NULL DEFAULT now(),

last_message_at timestamptz NOT NULL DEFAULT now(),

archived        boolean     NOT NULL DEFAULT false

);

CREATE TABLE IF NOT EXISTS agent_messages (

id              bigserial   PRIMARY KEY,

conversation_id uuid        NOT NULL REFERENCES agent_conversations(id) ON DELETE CASCADE,

turn            integer     NOT NULL,

role            text        NOT NULL CHECK (role IN ('user','assistant')),

content         jsonb       NOT NULL,

snapshot_at     timestamptz,

graph_loaded_at timestamptz,

created_at      timestamptz NOT NULL DEFAULT now()

);

CREATE TABLE IF NOT EXISTS agent_tool_calls (

id              bigserial   PRIMARY KEY,

message_id      bigint      NOT NULL REFERENCES agent_messages(id) ON DELETE CASCADE,

tool_name       text        NOT NULL,

input           jsonb       NOT NULL,

result_summary  jsonb       NOT NULL,

duration_ms     integer,

error           text

);

CREATE TABLE IF NOT EXISTS agent_usage (

id              bigserial   PRIMARY KEY,

conversation_id uuid        REFERENCES agent_conversations(id) ON DELETE SET NULL,

user_id         text        NOT NULL,

provider        text        NOT NULL,

model           text        NOT NULL,

input_tokens    integer     NOT NULL DEFAULT 0,

output_tokens   integer     NOT NULL DEFAULT 0,

provider_calls  integer     NOT NULL DEFAULT 0,

tool_iterations integer     NOT NULL DEFAULT 0,

validator_status text       CHECK (validator_status IN ('clean','repaired','flagged')),

created_at      timestamptz NOT NULL DEFAULT now()

);

CREATE INDEX IF NOT EXISTS idx_agent_conv_user     ON agent_conversations(user_id, last_message_at DESC);

CREATE INDEX IF NOT EXISTS idx_agent_msg_conv      ON agent_messages(conversation_id, turn);

CREATE INDEX IF NOT EXISTS idx_agent_tool_msg      ON agent_tool_calls(message_id);

CREATE INDEX IF NOT EXISTS idx_agent_usage_user    ON agent_usage(user_id, created_at DESC);

## 9.2 Notes on schema choices

- `provider_calls` is tracked separately from turns. On a free tier, requests per day is the binding

quota and one turn costs several requests. Without this column the team cannot see how close they are   to the ceiling.

- `content` stores the full provider-shaped message array, not extracted text. That is the shape the

next turn needs and it preserves the grounding chain the validators depend on.

- `result_summary` stores headline fields, not the whole payload. A rank_scenarios result over

every employee would otherwise make this table enormous.

## 9.3 Running and rolling back

Run via the existing backend/run_migrations.js, which uses DATABASE_URL. Rollback is four DROP TABLE IF EXISTS ... CASCADE statements; no organizational table is touched, so rollback is safe at any time.

# 10. Phase 1 — Foundation

Seven tasks. Exit criterion: a node -e script can resolve "Sarah" to Sarah Mitchell, print her glossary-annotated profile from a single frozen bundle, and reach the provider.

## 10.1 Provider dependency and configuration

Lane Backend · Depends on none · Estimate 0.5 d

Why. Everything else needs the key present and the flag readable, and the boot behaviour when the key is missing must be decided once rather than per-file.

Files. backend/package.json, backend/.env.example, render.yaml, backend/agent/config.js.

Steps.

- npm install @google/genai in backend/.

- Create agent/config.js exporting a frozen config object read from environment, with the defaults in

§7.4 applied.

- Add every new variable to .env.example with an explanatory comment, matching the existing style.

- Add the same variables to render.yaml with sync: false for the two secrets.

- Add a boot guard: when AGENT_ENABLED is true but the selected provider's key is absent, log a

clearly delimited banner and leave the agent routes unmounted. The rest of the API must start    normally.

Tests. agentConfig.unit.test.js — defaults applied; missing key with the flag on reports not-ready rather than throwing.

Done when the server boots with the flag off, with the flag on and a key, and with the flag on and no key, and the third case prints the banner and still serves every existing route.

## 10.2 Split computeAll into load and compute

Lane Backend · Depends on none · Estimate 0.5 d

Why. Invariant I-1. Today computeAll(supabase) loads roots internally, so obtaining both the raw bundle and the computed intelligence means reading the database twice — and the two reads can disagree.

Files. backend/domain/derived.js, backend/domain/index.js.

Contract.

/** Pure. Every analysis computed from one already-loaded bundle. */

function computeAllFromRoots(roots) { /* the current body of computeAll, minus the load */ }

/** Unchanged signature and behaviour. */

async function computeAll(supabase) {

return computeAllFromRoots(await loadRoots(supabase))

}

Steps.

- Move the body of computeAll after its loadRoots call into computeAllFromRoots(roots).

- Reduce computeAll to the two-line wrapper above.

- Export computeAllFromRoots from derived.js and expose it on

domain.intelligence.compute.allFromRoots.

Tests. Extend derived.unit.test.js: for a fixture bundle, computeAllFromRoots(roots) deep-equals the current computeAll output, ignoring the computedAt timestamp.

Done when the full suite passes with no behavioural change and both entry points exist.

## 10.3 domain/resolve.js — entity resolution

Lane Backend · Depends on none · Estimate 1 d

Why. Every other tool takes a resolved identifier rather than free text. This is the single control that removes the largest class of hallucination, and the logic already exists in voice.js — it needs lifting and generalising, not inventing.

Files. backend/domain/resolve.js, backend/domain/index.js.

Contract.

/**

* @param {object} roots      the frozen bundle

* @param {string} query      free text from the model

* @param {string} [type]     employee | agent | workflow | platform | knowledge | any

* @returns {{

*   candidates: Array<{

*     id: number|string, type: string, name: string,

*     role?: string, department?: string, criticality?: string,

*     confidence: 'high'|'medium'|'low'

*   }>,

*   ambiguous: boolean

* }}

*/

function resolveEntity(roots, query, type = 'any') {}

Steps.

- Port findEntity and findPerson from routes/voice/voice.js, keeping the two-stage strategy:

exact or substring match first, then token-overlap scoring against significant words with the generic    word stoplist (the, a, workflow, process, agent, bot, system, platform, tool).

- Generalise across all five namespaces read from the bundle.

- Return all candidates above threshold, never a silent single pick. Set ambiguous when two or

more score within a narrow band of each other.

- Resolve criticality through definitions.entityCriticality() — never read a raw column (I-4).

Tests. agentResolve.unit.test.js covering: exact full name; first name only; fuzzy multi-word; ambiguous surname returning two or more candidates; unresolvable text returning an empty list; and every case that voice.js handles today, so the lift is provably lossless.

Done when the tests pass and a surname shared by two employees returns both.

## 10.4 domain/metricGlossary.js

Lane Backend · Depends on none · Estimate 1 d

Why. "What does this number mean?" must be answered from the repository, not the model's priors. The definitions already exist as prose in derived.js and definitions.js; this turns them into data.

Contract.

{

metric: 'orgScore',

label: 'Organizational Intelligence Score (OIS)',

definition: 'Weighted composite of the three pillars: Governance Intelligence (0.35), ...',

range: '0-100',

bands: { '85+': 'STRONG', '65-84': 'PARTIAL', '40-64': 'WEAK', '<40': 'CRITICAL' },

authored: true,

authoredNote: 'Weights are authored, not measured (D-11). Nothing in the source data defined them.',

computedIn: 'backend/domain/derived.js :: pillars()',

decisions: ['D-02', 'D-11'],

}

Steps.

- Transcribe an entry for every metric any tool can return. Do not paraphrase from memory — read the

doc comment above each function in derived.js and definitions.js and transcribe it.

- Set authored: true wherever the formula is a product judgement rather than a measurement. At

minimum: the GI/MI/DI pillar weights, the platform-criticality derivation, and the tool-risk    composite.

- Export a lookup by metric name and the full list.

Tests. metricGlossary.unit.test.js — every metric name reachable through a tool result has an entry. This test is load-bearing: it is what stops the glossary rotting as metrics are added. It will initially need a hardcoded list of metric names; from 11.2 onward it should derive them from the tool registry.

Done when coverage is complete and the authored flags are correct.

## 10.5 Migration

Lane Data · Depends on none · Estimate 0.5 d

Write backend/sql/15_agent_layer.sql exactly as §9.1. Apply it via run_migrations.js. Verify the four tables and four indexes exist, that the foreign keys cascade, and that the role and validator_status check constraints reject bad values.

Done when an insert-and-cascade-delete round trip works against the real database.

## 10.6 agent/turnContext.js

Lane Backend · Depends on 10.2 · Estimate 0.5 d

Why. This is invariant I-1 made concrete. It is the only place in the agent layer permitted to read the database for organizational data.

Contract.

/**

* @returns {{

*   roots: object, intel: object,

*   snapshotAt: string, graphSource: object, graphStale: boolean

* }}

*/

async function buildTurnContext() {}

Steps.

- loadRoots(supabase) once; computeAllFromRoots(roots) once.

- Capture domain.graph.source() and stamp snapshotAt.

- Set graphStale when the graph's loadedAt trails snapshotAt by more than a configured threshold

(default six hours). This surfaces the graph-versus-roots snapshot hazard rather than hiding it.

- Export a frozen object. Tools receive it; they never re-read.

Tests. turnContext.unit.test.js with a stubbed Supabase — asserts exactly one loadRoots call and that graphStale flips correctly around the threshold.

Done when a turn provably issues one organizational read.

## 10.7 Provider adapter and Gemini implementation

Lane Backend · Depends on 10.1 · Estimate 2 d · Decision D-74, D-76

Why. Invariant I-7, and the reason the free-versus-paid choice stays reversible.

Files. backend/agent/providers/{index,gemini}.js.

Steps.

- Implement the interface in §8.4 exactly.

- Build gemini.js on @google/genai, using the streaming content generation path with explicit

history rather than any server-side conversation state. We keep conversation state ourselves —    the audit trail, tool trace and validator all depend on our own record, and splitting state across    two systems would fragment it.

- Map Gemini's function-call parts to { type: 'tool_call', id, name, args } and text parts to

{ type: 'text', text }.

- Map tool schemas to the OpenAPI subset Gemini accepts. Keep schemas flat; avoid nested objects and

deep arrays.

- Classify errors into retryable (429, 5xx, transport) and terminal, and surface retryable on the

error event so the loop can decide.

- Honour AbortSignal so a disconnected client stops the stream.

Tests. provider.unit.test.js against a stubbed transport — event normalisation, tool call mapping, error classification, abort propagation. No live calls in CI.

Done when a scripted single-tool exchange completes against the live free tier from a local script, and the same test passes offline against the stub.

# 11. Phase 2 — The agent turn

Nine tasks. Exit criterion: an authenticated curl against the SSE endpoint streams a grounded, validated answer to "who carries the most key-person risk and why?"

## 11.1 Tool registry, envelope and input validation

Lane Backend · Depends on 10.6 · Estimate 1.5 d

Why. One shape for every tool result, and — because Gemini offers no strict-mode guarantee (§3.3) — one place where arguments are validated before any tool body runs.

Contract. Every tool module exports:

{

name: 'get_entity_profile',

description: 'Call this when the user asks about one specific person, agent, workflow or tool...',

parameters: { type: 'object', properties: { ... }, required: [...] },

run(ctx, args) { /* ctx is the frozen turn context */ },

}

Every result is wrapped by the registry, never by the tool:

{

data:       { /* the MVP's real computed object, unmodified */ },

provenance: { computedAt, snapshotAt, source: 'live'|'graph', inputs: {...}, graphLoadedAt? },

evidence:   { status: 'computed'|'insufficient_evidence', coverage, covered, total } | null,

authored:   false,

notes:      [ /* caveats the model must surface */ ],

}

Steps.

- Build the registry: assemble tools, bind the frozen context, expose provider-shaped declarations.

- Implement argument validation against each tool's schema — required fields, types, enum membership.

A violation returns a structured tool error to the model so it can correct itself; it never throws    into the loop.

- Implement the envelope wrapper, including automatic provenance stamping from the turn context.

- Enforce a result size cap; truncate long arrays with an explicit truncated note rather than

silently.

Tests. agentRegistry.unit.test.js — envelope shape; enum rejection; required-field rejection; truncation notes present.

Done when a tool cannot return an unwrapped result and a bad argument produces a correctable error.

## 11.2 Read tools

Lane Backend · Depends on 11.1, 10.3, 10.4 · Estimate 2 d

Implements tools 1 through 7: resolve_entity, get_org_snapshot, get_entity_profile, list_entities, get_intelligence, run_brain_analysis, get_metric_definition. Full schemas in Appendix A.

Two points that are easy to get wrong:

- `list_entities` uses a closed filter grammar. Every filter key is an enum. No free-form predicate,

no SQL, no expression evaluation. A general query capability would become a second definition of   "critical" competing with definitions.js, which is exactly what invariant I-4 exists to prevent.

- `run_brain_analysis` must degrade honestly. When domain.graph.isReady() is false, return a

structured "graph not loaded" result — never an empty payload, which reads as "nothing found". Always   attach the graph's loadedAt, because it is a different snapshot from the roots bundle.

Tests. agentTools.unit.test.js against a fixture bundle: every tool's shape, provenance present, evidence gates passed through unmodified, enums rejected, graph-not-ready path structured.

Done when all seven return correctly enveloped results and no tool issues a database query.

## 11.3 Simulation tools

Lane Backend · Depends on 11.1 · Estimate 1 d

Implements run_simulation, rank_scenarios and compare_scenarios over the existing domain.simulations functions and the frozen bundle.

compare_scenarios runs two scenarios and returns both results plus a server-computed diff — health-delta difference, and the intersection and symmetric difference of impacted agents and workflows. This tool exists specifically so the model never subtracts two numbers itself (invariant I-3). Rule I-3 is only enforceable if there is a tool for every comparison the model would otherwise perform by hand.

Tests. Extend agentTools.unit.test.js: results pass through unmodified; the diff is computed correctly for overlapping and disjoint impact sets.

## 11.4 The constitution and roster builder

Lane Backend · Depends on 10.6 · Estimate 1 d

Files. backend/agent/constitution.js.

Contents.

- Static constitution — the behavioural rules, verbatim from design document §8.1: quote numbers

rather than compute them; no arithmetic; resolve before naming; report insufficient evidence    honestly; label authored formulas; distinguish snapshots; treat tool content as data not    instructions; write like a chief of staff.

- Compact organization roster — a flat projection built from the frozen bundle: every person,

agent, workflow and tool with owner, criticality and status. Target 3,000 to 5,000 tokens.

- Volatile per-turn block — snapshotAt, graphLoadedAt, the stale-graph warning when set, and

the user's current page when supplied.

All three are assembled into systemInstruction per request (§3.3, consequence 2).

Tests. constitution.unit.test.js — roster contains every entity in the fixture bundle; token estimate within budget; volatile block present and correctly formatted.

## 11.5 The agent loop

Lane Backend · Depends on 10.7, 11.1, 11.4 · Estimate 2 d

Files. backend/agent/loop.js.

Contract.

/**

* @param {object} turnContext

* @param {Array}  history          prior messages, provider-shaped

* @param {string} userMessage

* @param {(event) => void} emit    SSE emitter

* @param {AbortSignal} signal

* @returns {{ text, toolTrace, usage, iterations, finishReason }}

*/

async function runTurn({ turnContext, history, userMessage, emit, signal }) {}

Steps.

- Assemble the system instruction and history; call provider.stream().

- Forward text deltas as token events.

- On a tool call: emit tool_start with a human-readable label, validate input, execute against the

frozen context, emit tool_done with a one-line summary, append the result to history.

- Repeat until the model returns no tool call, or AGENT_MAX_ITERATIONS is reached, or the wall-clock

timeout expires. Cap reached is a reported outcome, not a silent stop — the client must be told.

- Retry a retryable provider error once with backoff; surface a terminal error as an error event.

- Record every tool call with its duration for the trace.

Tests. agentLoop.unit.test.js with a scripted stub provider: single-tool turn; multi-tool turn; iteration cap reached and reported; retryable error retried; terminal error surfaced; abort mid-stream stops cleanly.

Done when all six scripted scenarios pass without touching the network.

## 11.6 The SSE route

Lane Backend · Depends on 11.5 · Estimate 1.5 d

Files. backend/routes/agent/{index,chat}.js, backend/index.js (one mount line).

Steps.

- Mount at /api/agent, below the existing global requireAuth. **Mount only when AGENT_ENABLED is

true and the provider is ready** — otherwise the routes do not exist, which is a cleaner failure than    a 500.

- Open the stream with the headers in Appendix B and write an immediate first byte. This is what stops

a cold Render instance from looking like a hang.

- Emit ready, then delegate to runTurn.

- Start a fifteen-second heartbeat so intermediaries do not close an idle stream during a long tool

phase.

- On req.on('close'), abort the provider stream so tokens are not consumed for a disconnected client.

- Emit done with the navigation offer, tool trace, provenance and usage.

Tests. agentRoutes.test.js, provider stubbed, runs offline: 401 without a token; correct event order; heartbeat present; abort cleans up; flag off means 404.

## 11.7 Rate limiting, budget and usage accounting

Lane Backend · Depends on 10.5, 11.6 · Estimate 1 d

Why. On a free tier, requests per day is the binding constraint (§3.3). Without a budget one developer's test loop can exhaust the whole project's daily quota before a demo.

Steps.

- Apply the existing middleware/rateLimit.js with keyFn: req => req.user.sub. The middleware

already supports this; no change to it is required.

- Before each turn, count today's turns for the user from agent_usage; return 429 with a clear

message and a reset time when over AGENT_DAILY_TURN_BUDGET.

- After each turn, write an agent_usage row including provider_calls.

- Expose GET /api/agent/quota returning the user's remaining budget, so the UI can warn before the

user hits it.

Known limitation to document, not fix: the in-process rate limiter does not survive a restart or span instances. This is already documented in the middleware's own header and is acceptable for a single-instance deployment. The daily budget, being database-backed, does not share this weakness.

Tests. Extend agentRoutes.test.js — budget exhaustion returns 429; a usage row is written per turn.

## 11.8 Validators

Lane Backend · Depends on 11.5 · Estimate 1.5 d · Decision D-73

Files. backend/agent/validators.js.

Numeric citation validator.

- Walk every tool result from the turn, collecting all numeric literals — including numbers inside

strings — into an allowed set, and record the longest array length returned.

- Extract numeric tokens from the assistant's final text.

- A number passes if it is in the allowed set; within 0.5 of a member, for rounding; an integer no

greater than the longest array length, covering legitimate counts and ordinals; a four-digit year    present in the results; or inside a quoted entity name.

- Anything else is a violation.

- On violation, one automatic repair round: re-prompt with the specific unverified figures named,

asking for a corrected answer using only cited values. If the second attempt still fails, return the    answer annotated as containing unverified figures and record validator_status = 'flagged'.

Entity allowlist validator. Build the allowed set from the frozen bundle — employees, agents, workflows, platforms, knowledge assets, departments. Flag capitalised multi-word sequences that look like names and are not in the set. A warning, not a block: English capitalisation is too noisy to block on.

This repository has already been burned by this exact failure. frontend/lib/search.ts carries a comment about replacing a fixture containing a fake workflow and a fake person "neither of which exist anywhere else in the app", and voice.js's header documents the same class of bug with five invented names. A language model will reproduce it unless something checks.

Tests. agentValidator.unit.test.js — catches an invented figure; passes a quoted figure; passes rounding within 0.5; passes an ordinal within list length; passes a year present in results; flags an invented person; does not flag a real one; does not flag ordinary capitalised English.

## 11.9 Conversation persistence

Lane Backend · Depends on 10.5, 11.6 · Estimate 1 d

Load prior history for a conversation, append the user and assistant turns, write the tool trace, and apply a sliding window bounded by token budget. When the window drops turns, replace them with a short summary rather than deleting them silently, so the model is not left reasoning over an invisible gap.

Set the conversation title from the first user message, truncated.

Tests. agentPersistence.unit.test.js with stubbed Supabase — round trip preserves tool-call blocks; the window drops oldest first; the summary replaces rather than deletes.

# 12. Phase 3 — Frontend and navigation

Seven tasks. Exit criterion: ask a question on the dashboard, accept the navigation offer, land on the right page with the right block flashing and the explanation still on screen.

## 12.1 Extract the single navigation path

Lane Frontend · Depends on none · Estimate 0.5 d

Why. GlobalSearchOverlay.tsx's go() already implements navigate-plus-focus correctly. The agent must reuse it, not add a second implementation — the repository's established pattern for exactly this situation is lib/deriveCollaborations.js and lib/ownerBackups.js.

Steps.

- Create frontend/lib/navigate.ts exporting goToTarget({ page, match }), containing the existing

logic verbatim: same-route fast path via history.replaceState, otherwise router.push with the    ?focus= query, then requestFocus(match) in both cases.

- Refactor GlobalSearchOverlay.tsx to call it. In the same commit, so this is a deduplication

rather than a second implementation.

Tests. tsc --noEmit clean; command palette navigation manually verified unchanged, including the same-route case.

## 12.2 Navigation catalog and propose_navigation

Lane Backend · Depends on 11.1 · Estimate 1 d · Decision D-71

Steps.

- **First, test whether Vercel's build with rootDir: frontend can resolve a JSON file at the

repository root.** This determines the approach and takes an hour.

- If it resolves: move the catalog seeds — pages, section headings, module codes — into

shared/navigation-catalog.json, and have both backend/domain/navigationCatalog.js and    frontend/lib/commandIndex.ts read from it. One source.

- If it does not: keep the two copies and add navigationCatalog.unit.test.js, which parses both and

fails on divergence. Document the duplication in both files, following the precedent already set by    frontend/lib/evidenceGate.ts. Silent duplication is not acceptable in either case.

- Implement propose_navigation, which validates the page and section against the catalog and returns

an offer object. An unknown page or unverified heading is a tool error returned to the model so it    can correct itself — never a link that 404s or scrolls nowhere.

Done when an invalid target is rejected and a valid one produces a correct ?focus= href.

## 12.3 The SSE client

Lane Frontend · Depends on 11.6 · Estimate 1 d

frontend/lib/agentClient.ts — a fetch plus ReadableStream reader, because the endpoint requires an Authorization header and the browser's native EventSource cannot send one. Parses the protocol in Appendix B, exposes an async iterator of typed events, and supports abort via AbortController.

Handle a truncated stream — network drop mid-turn — by surfacing a clear error rather than leaving a half-rendered message.

## 12.4 Agent provider and shell mount

Lane Frontend · Depends on 12.3 · Estimate 1 d

AgentProvider.tsx holding messages, streaming state, conversation identifier, and send / abort.

Mount it in `AppShell.tsx`, alongside `GlobalSearchOverlay` and `DeepLinkFocus` — not inside `app/page.tsx`. If the panel lives only on the dashboard, navigating to /risk destroys the conversation that sent the user there, which defeats the navigation feature entirely.

Gate rendering on NEXT_PUBLIC_AGENT_ENABLED.

## 12.5 Panel, message and composer

Lane Frontend · Depends on 12.4 · Estimate 2 d

Three display modes: expanded and hero-sized above the dashboard grid on `/`, docked to the right elsewhere, collapsible to a pill.

- Stream text token by token, buffered to roughly 30 ms frames to avoid thrashing React.

- Render tool_start as a live status line — "Running simulation — Sarah Mitchell leaves…". On a

multi-tool turn this is most of what the user sees for the first several seconds, and it is genuinely   informative rather than a spinner.

- A stop button that aborts client and server.

- Follow the existing design tokens in globals.css. Do not introduce a new palette.

## 12.6 Tool trace and navigation offer

Lane Frontend · Depends on 12.5, 12.2 · Estimate 1 d

ToolTrace.tsx — a collapsible "How I got this" listing each tool call, its key inputs, a one-line result summary and the timestamps. This is the honest presentation, it matches the existing EvidenceBadge and TruthBadge provenance culture, and in practice it is the strongest deterrent to trusting a wrong answer: a claim with no supporting call is visibly unsupported.

NavigationOffer.tsx — renders the offer as a button calling goToTarget from 12.1. The agent never navigates on its own. Also render the validator warning banner when validator_status is flagged.

## 12.7 get_page_context and page metric wiring

Lane Backend · Depends on 12.2 · Estimate 1.5 d

domain/pageContext.js — given a route, return its section list plus the current value of each section's headline metric, from the same frozen bundle the page itself would fetch.

This is what makes "explain what I'm seeing" grounded rather than a generic page description, and it is the difference between a chatbot that links to a page and one that walks the user through it.

Tests. Every catalog section either has a mapped metric or is explicitly marked as having none. No section may silently return nothing.

# 13. Phase 4 — Succession and hardening

Five tasks. Exit criterion: the full acceptance demo in §2.3 runs end to end on live data.

## 13.1 employeeLeavesWithSuccessor

Lane Backend · Depends on 10.2 · Estimate 2 d · Decision D-70 — blocking

Why. This is the flagship capability and the only genuine gap in the existing domain layer. Nothing in the codebase today models a handover.

Files. backend/domain/simulations.js.

Contract.

/**

* @returns {{

*   scenario, targetType, targetId, targetName,

*   successorId, successorName,

*   impactedAgents, impactedWorkflows, impactedPeople,

*   severity, healthDelta,

*   residualRisk: {

*     assetsWithoutBackup: Array,

*     assetsUndocumented: Array,

*     successorConcentrationAfter: number,

*     successorBecomesSpof: boolean

*   },

*   comparedToNoSuccessor: { healthDelta, severity }

* }}

*/

function employeeLeavesWithSuccessor(employeeId, successorId, roots) {}

Mutation policy — assumed under D-70, confirm before implementing:

- Reassign agents.owner_id, knowledge_assets.owner_id and workflow_runbooks.owner_id from the

departing employee to the successor.

- Reassign the departing employee's accountability_links.

- Backup coverage does not transfer. Where owners.backup_owner named the departing person, it

becomes null. A backup that named the person who left is not coverage, and carrying it over would    fabricate a signal that invariant I-6 and decision D-07 exist to prevent.

- Documentation state does not transfer. An undocumented asset remains undocumented under a new

owner; that is the entire meaning of the metric.

- The successor's existing load counts. Report their concentration after the transfer, not merely

the vacancy being filled. The interesting executive finding is usually that a single point of failure    was solved by creating a larger one.

Reuse cloneRoots(), recount(), healthDelta() and orgHealth(). Do not introduce a second health formula.

Tests. simulationsReassign.unit.test.js — backup does not transfer; documentation does not transfer; successor concentration rises correctly; successorBecomesSpof fires when the successor crosses the SPOF condition via spofVerdict(); the health delta sign is correct; an unknown successor returns null rather than throwing.

## 13.2 The simulate_reassignment tool

Lane Backend · Depends on 13.1, 11.3 · Estimate 0.5 d

Expose it through the registry. Update the constitution to describe when to reach for it — specifically, that a question of the form "what if X takes over from Y" is a reassignment, not two separate scenarios.

## 13.3 Graph staleness surfacing

Lane Backend · Depends on 10.6, 11.2 · Estimate 0.5 d

The knowledge graph loads once at boot and is refreshed only by the manual reload endpoint, while roots are read every turn. Graph-derived and roots-derived figures are therefore different snapshots, and the agent is the first component capable of putting both in one sentence.

- Attach graphLoadedAt to every graph-backed tool result.

- When turnContext.graphStale is set, add a line to the volatile system block instructing the model to

attribute graph-derived figures to their load time.

- Log a warning server-side so operations can see it.

## 13.4 Golden-question regression suite

Lane Backend · Depends on 13.2 · Estimate 1.5 d

A fixed set of roughly twenty questions with expected grounding — which tools should be called, which entities should appear, and that the numeric validator reports clean. Run against a stub provider in CI for the deterministic parts, and against the live provider manually before any release.

This is the only mechanism that will catch quality regression when the model, the prompt, or a tool description changes. Without it, prompt tuning is guesswork. It is also the instrument that would let the team evaluate a local model objectively if the free tier ever becomes limiting.

## 13.5 Fallback, flag and documentation

Lane Backend · Depends on all · Estimate 2 d · Decision D-72

- When AGENT_ENABLED is false, the frontend hides the panel and the existing command palette remains

the primary interface. voice.js and executive.js stay mounted as the non-LLM fallback.

- Update README.md and BACKEND_INTEGRATION.md with the agent surface.

- Add the W-L row to the workstream map in the decision log, and close D-69 through D-76 there.

- Correct the stale row in the decision log's deferred table — it still lists

lib/knowledgeRisk.ts and lib/aiToolIntelligence.ts as having no backend score to point at, but    D-58 and D-59 closed both during W-K.

# 14. Error handling and failure modes

Every row is a case the team must handle deliberately. The default of "surface a 500" is wrong for most of them.

| Failure | Detection | Behaviour | User sees |
| --- | --- | --- | --- |
| Provider key missing | Boot | Routes not mounted; banner logged | Agent UI hidden |
| Provider 429 (quota) | Error event | No retry; end turn | "Daily capacity reached, resets at midnight Pacific" |
| Provider 5xx or transport | Error event | One retry with backoff, then end | "The model is temporarily unavailable" |
| Turn budget exhausted | Pre-flight | 429 before any provider call | Remaining budget and reset time |
| loadRoots fails | Turn context | Abort turn | "Cannot read organizational data right now" — never a partial answer |
| Graph not loaded | Tool call | Structured not-ready result | Agent says the analysis is unavailable and why |
| Evidence gate insufficient | Tool result | Passed through | "Not measured — coverage is 32 percent" |
| Tool throws | Registry | Structured error to the model | Agent retries or explains the gap |
| Bad tool arguments | Registry validation | Correctable error to the model | Usually invisible; model self-corrects |
| Iteration cap reached | Loop | Stop and report | "I reached my step limit — here is what I found so far" |
| Turn timeout | Loop | Abort and report | Partial answer with a clear note |
| Numeric validator flags | Post-turn | One repair round, then annotate | Warning banner on the message |
| Client disconnects | req.on('close') | Abort provider stream | Nothing |
| Stream truncated | Client | Surface error | "The response was interrupted" |

The rule behind this table: a failure must never be presentable as an answer. The most dangerous outcome in this product is not an error — it is a confident, complete-looking response built on missing data. That is the failure mode routes/executive/executive.js's own header warns about, and it applies with more force to a fluent model than to a template.

# 15. Observability

Log per turn, structured, at info level: conversation and turn identifiers, user, provider and model, tool names in call order with durations, provider call count, token usage, validator status, finish reason, and total duration.

Log at warn level: retries, iteration cap reached, validator repair rounds, stale graph, budget refusals.

Never log: the API key, full message content, or full tool payloads. Tool names and result summaries only — this is an organizational intelligence product and conversation content is sensitive even when the underlying dataset is a demo.

agent_usage is the system of record for quota and cost. Build one query the team can run to see turns per day, provider calls per day, and flagged-validator rate.

# 16. Security checklist

Verify every item before enabling the flag in production.

- API key present only in backend/.env and the Render dashboard. Not in git, not in any

NEXT_PUBLIC_ variable, never returned by an endpoint.

- /api/agent sits below the existing requireAuth. No unauthenticated path exists.

- No tool performs a write to any organizational table (invariant I-2). Verify by grep, not by memory.

- Tool results are delimited in the prompt and framed as data, not instructions. Organizational free-text

fields — decision descriptions, incident lessons, truth claims, entity names — reach the model and    could in principle carry planted instructions. The constitution instructs the model to quote and flag    such content rather than act on it, and because no tool writes, the worst outcome is a wrong answer    rather than a state change.

- Rate limit and daily budget both active.

- Conversations are scoped by user_id on read as well as write. A user must not be able to load

another user's conversation by guessing an identifier.

- CORS unchanged — the existing allowlist already covers the agent route.

- SSE responses set Cache-Control: no-cache, no-transform.

# 17. Performance and quota budget

## 17.1 Latency targets

| Phase | Target |
| --- | --- |
| First SSE byte | Under 100 ms, excluding cold start |
| loadRoots | 200 to 400 ms — 21 parallel reads |
| First token | 1 to 3 s |
| Each tool call | 2 to 20 ms — in-process over the frozen bundle |
| Full answer, three tool calls | 6 to 12 s |

A cold Render free instance adds 30 to 60 seconds. The immediate first byte and the tool status stream are what make this survivable rather than appearing broken.

## 17.2 Quota budget — fill in on day one

The team lead records the actual observed limits here after checking AI Studio (§7.1).

| Quantity | Limit | Notes |
| --- | --- | --- |
| Requests per minute | to be confirmed |  |
| Tokens per minute | to be confirmed | Must exceed roughly 15,000 for one comfortable turn |
| Requests per day | to be confirmed | The binding constraint |
| Provider calls per turn | 2 to 9 | One, plus one per tool round |
| Implied turns per day | derived | Requests per day divided by average calls per turn |

Set AGENT_DAILY_TURN_BUDGET so that the number of active users multiplied by the budget stays comfortably under the implied daily ceiling.

# 18. Testing strategy

## 18.1 Suites

All are added to backend/tests/run-all.js, following the existing convention: pure and stubbed suites run in CI, live suites self-skip when their environment variables are absent.

| Suite | Kind | Covers |
| --- | --- | --- |
| agentConfig.unit | pure | Configuration defaults and the missing-key path |
| agentResolve.unit | pure | Resolution, including ambiguity and the lifted voice.js cases |
| metricGlossary.unit | pure | Every reachable metric has an entry |
| turnContext.unit | stubbed | Exactly one roots read; stale-graph detection |
| provider.unit | stubbed | Event normalisation, error classification, abort |
| agentRegistry.unit | pure | Envelope, argument validation, truncation |
| agentTools.unit | pure | All thirteen tools over a fixture bundle |
| agentLoop.unit | stubbed | Six loop scenarios including cap and abort |
| agentValidator.unit | pure | Numeric and entity validation, both directions |
| agentPersistence.unit | stubbed | History round trip and windowing |
| agentRoutes | stubbed HTTP | Auth, event order, heartbeat, budget, flag off |
| navigationCatalog.unit | pure | Catalog integrity or drift, per D-71 |
| simulationsReassign.unit | pure | The full D-70 mutation policy |
| agentGolden.live | live, skipping | The golden-question suite against the real provider |

## 18.2 The golden-question suite

Roughly twenty questions spanning: single entity lookup, org-level summary, a metric explanation, a simulation, a comparison, a reassignment, an ambiguous name, a question whose data is genuinely missing, and a follow-up chain. Each asserts the tools called, the entities named, and a clean validator verdict.

Run it before every release and after any change to a prompt, a tool description, or the model identifier. A tool description is production behaviour in this system, not a comment.

## 18.3 Manual QA script

The acceptance demo in §2.3, executed in a real browser against live data, plus: refresh mid-conversation and confirm history restores; navigate away mid-stream and confirm the stream aborts; exhaust the budget and confirm the message is clear; disable the flag and confirm the app is unchanged.

# 19. Deployment

## 19.1 Order of operations

Strictly sequential. Each step is independently reversible.

- Migration. Apply 15_agent_layer.sql. Additive only; safe with the current backend running.

- Backend with the flag off. Deploy to Render with AGENT_ENABLED=false. Routes are not mounted,

so this is a no-op deployment that only proves the build works with the new dependency.

- Set secrets. Add GEMINI_API_KEY and the agent variables in the Render dashboard.

- Enable the backend flag. Set AGENT_ENABLED=true and restart. Verify with authenticated curl

against the SSE endpoint before any frontend change.

- Frontend with the flag off. Deploy to Vercel with NEXT_PUBLIC_AGENT_ENABLED=false.

- Enable the frontend flag. The UI appears.

## 19.2 Platform configuration

Render. Add the agent variables to render.yaml with sync: false for secrets. NODE_VERSION stays at 22. Note that the free plan spins down after inactivity with a 30 to 60 second cold start — acceptable for internal use, poor for a live demo. Decision D-75 covers upgrading before any customer sees this.

Vercel. One new variable, NEXT_PUBLIC_AGENT_ENABLED. If D-71 resolves toward a shared catalog file at the repository root, confirm the build still succeeds with rootDir: frontend.

## 19.3 Post-deploy verification

- GET / returns service metadata — the existing routes are unaffected.

- An existing endpoint such as /api/health/summary still answers correctly.

- GET /api/agent/quota returns a budget for an authenticated user.

- One full turn over curl returns the correct event sequence and ends with done.

- The tool trace is populated and the validator status is clean.

- An agent_usage row was written.

- The dashboard renders the panel and one question answers end to end.

## 19.4 Rollback

Set AGENT_ENABLED=false and restart. The routes disappear; nothing else in the product is affected. This is the entire rollback procedure for the feature. The migration need not be reversed — the tables are inert when unused — but if desired, four cascading drops remove them without touching organizational data.

# 20. Operations runbook

## 20.1 Daily quota exhausted

Symptom: turns fail with a provider 429 late in the day. Confirm against agent_usage provider calls for the day. Options, in order of preference: lower AGENT_DAILY_TURN_BUDGET; lower AGENT_MAX_ITERATIONS, since capped turns consume the most requests; or switch AGENT_PROVIDER to a paid provider for the remainder of the day. The last is a single environment variable because of the adapter.

## 20.2 Quota monitoring

Track daily: total turns, total provider calls, calls per turn, and flagged-validator rate. A rising calls-per-turn figure means the model is taking more steps than it needs — usually a symptom of an unclear tool description, not of the model.

## 20.3 Validator flagging spike

A sudden rise in validator_status = 'flagged' means the model has started producing uncited figures. Most likely causes, in order: a tool description changed and the model is guessing where it used to call; the model identifier rolled to a new version; or a tool started returning a shape the model misinterprets. Check the golden-question suite first — it is designed to localise exactly this.

## 20.4 Switching to a paid provider

Set AGENT_PROVIDER=anthropic, set ANTHROPIC_API_KEY, set AGENT_MODEL, restart. Run the golden suite. Recommended before any customer-facing demo: answer quality is the product in this feature, and the cost of a demo session is a few tens of cents.

## 20.5 Kill switch

AGENT_ENABLED=false plus a restart. Under a minute. Every other feature of the product is unaffected.

# 21. Risk register

| # | Risk | Likelihood | Impact | Mitigation |
| --- | --- | --- | --- | --- |
| 1 | Free-tier daily quota too small for a team plus demos | High | Medium | Per-user budget from day one; adapter allows same-day switch |
| 2 | Flash-tier reasoning too weak for the four-turn chain | Medium | High | Golden suite measures it objectively; adapter allows upgrade. Assess at the end of Phase 2, not at the end of the project |
| 3 | Model identifier rolls and breaks the deployment | Medium | Medium | Identifier is an environment variable; pin explicitly rather than using an alias |
| 4 | Metric glossary rots as metrics are added | Medium | Medium | The coverage test is load-bearing and must not be skipped |
| 5 | Prompt injection via organizational free text | Low | Medium | Data framing, no writes, operator instructions in the system channel only |
| 6 | Render cold start ruins a demo | High | Low | Immediate first byte; warm before demos; D-75 |
| 7 | Graph and roots snapshots blended in one answer | Medium | Medium | Task 13.3 |
| 8 | Frontend type errors ship, since ignoreBuildErrors is on | Medium | Low | CI typecheck must pass for agent code regardless of the flag |
| 9 | D-70 not decided, blocking Phase 4 | Medium | High | Escalate before Phase 1 completes; Phases 1–3 are unaffected |

# 22. Timeline

Three engineers, three weeks.

| Week | Backend A | Backend B | Frontend |
| --- | --- | --- | --- |
| 1 | 10.1, 10.2, 10.6, 10.7 | 10.3, 10.4, 10.5 | 12.1, then design review |
| 2 | 11.1, 11.2, 11.5 | 11.3, 11.4, 11.8 | 12.3, 12.4, 12.5 |
| 3 | 11.6, 11.7, 11.9, 13.3 | 12.2, 12.7, 13.1, 13.2 | 12.6, QA |
| Buffer | 13.4, 13.5, deployment, acceptance demo |  |  |

Checkpoint at the end of week 2: run the golden-question suite against the free tier. If reasoning quality is inadequate, that is the moment to switch providers — before the frontend work is tuned around a particular model's behaviour.

# Appendix A — Tool catalog

All thirteen. Schemas are the OpenAPI subset Gemini accepts: flat objects, enumerated strings, no deep nesting.

| # | Tool | Parameters | Returns |
| --- | --- | --- | --- |
| 1 | resolve_entity | query string; type enum | Candidates with confidence; ambiguity flag |
| 2 | get_org_snapshot | none | OIS and pillars (authored), org health, coverage, counts |
| 3 | get_entity_profile | type enum; id string | Ownership, SPOF verdict, documentation, predicted risk, dependencies, workflows, knowledge, RACI, continuity |
| 4 | list_entities | type enum; criticalityAtLeast enum; hasBackup boolean; documented boolean; status enum; department string; ownedBy string; sort enum; limit integer | Filtered list |
| 5 | get_intelligence | area enum of thirteen derived products | The full computed object with its evidence gate |
| 6 | run_brain_analysis | analysis enum of live module slugs | Payload, confidence, recommendations, graph load time |
| 7 | get_metric_definition | metric enum | Definition, range, bands, authored flag, source location |
| 8 | run_simulation | scenario enum of four; targetId string | Impacted sets, severity, health delta, baseline and simulated scores |
| 9 | rank_scenarios | limit integer | Worst-first ranking |
| 10 | compare_scenarios | two scenario descriptors | Both results plus a server-computed diff |
| 11 | simulate_reassignment | fromEmployeeId; toEmployeeId | Handover result, residual risk, comparison against no successor |
| 12 | get_page_context | page enum of routes | Sections with current headline metric values |
| 13 | propose_navigation | page enum; section string; reason string | Validated offer with href, or a tool error |

Writing tool descriptions. Be prescriptive about when to call, not merely what the tool does. "Call this when the user asks about one specific named person, agent, workflow or tool" outperforms "Returns an entity profile." Tool descriptions are production behaviour and belong in code review.

# Appendix B — SSE protocol

Response headers

Content-Type: text/event-stream

Cache-Control: no-cache, no-transform

Connection: keep-alive

X-Accel-Buffering: no

Write :\n\n immediately on open, before any work, so the client sees life during a cold start.

Events

| Event | Payload | When |
| --- | --- | --- |
| ready | { conversationId, snapshotAt } | Immediately after the turn context is built |
| token | { text } | Each text delta |
| tool_start | { id, name, label } | Before a tool executes; label is human-readable |
| tool_done | { id, name, summary, durationMs } | After it returns |
| warning | { code, message } | Stale graph, iteration cap, validator flag |
| done | { text, toolTrace, navigationOffer, provenance, usage, validatorStatus } | End of turn |
| error | { code, message, retryable } | Terminal failure |

Heartbeat: :\n\n every fifteen seconds while the stream is open.

# Appendix C — Environment variables

| Variable | Scope | Secret | Default | Notes |
| --- | --- | --- | --- | --- |
| AGENT_ENABLED | Backend | No | false | Master flag; routes unmounted when false |
| AGENT_PROVIDER | Backend | No | gemini | Selects the adapter |
| AGENT_MODEL | Backend | No | gemini-3.7-flash | Never hardcode; confirm the current free row |
| GEMINI_API_KEY | Backend | Yes | — | Render sync: false |
| ANTHROPIC_API_KEY | Backend | Yes | — | Only when the provider is Anthropic |
| AGENT_MAX_ITERATIONS | Backend | No | 8 | Tool rounds per turn |
| AGENT_TURN_TIMEOUT_MS | Backend | No | 120000 | Wall clock per turn |
| AGENT_DAILY_TURN_BUDGET | Backend | No | 40 | Per user per day |
| AGENT_GRAPH_STALE_HOURS | Backend | No | 6 | Stale-graph warning threshold |
| NEXT_PUBLIC_AGENT_ENABLED | Frontend | No | false | Shows or hides the panel |

Existing variables are unchanged: SUPABASE_URL, SUPABASE_KEY, DATABASE_URL, PORT, JWT_SECRET, TOKEN_TTL, ADMIN_EMAIL, ADMIN_PASSWORD, ADMIN_ORG, CORS_ORIGINS, NEXT_PUBLIC_API_URL.

# Appendix D — Glossary

For engineers new to this codebase.

| Term | Meaning |
| --- | --- |
| Roots | The 21 source tables holding facts maintained outside this codebase. loadRoots() reads them in one parallel batch. Everything derived is a pure function of this bundle. |
| Derived intelligence | The computed summaries in domain/derived.js — accountability, collaboration, predictive risk, pillars, org health and others. Formerly frozen database rows; now computed on demand with provenance. |
| The brain | backend/brain/ — a knowledge graph plus 51 analyses, module codes M01 to M55. A library, not a service. Reached through domain.graph.run(). |
| Evidence gate | The mechanism that returns "insufficient evidence" plus coverage instead of a number when too little data supports a score. |
| SPOF | Single point of failure. Defined once, in definitions.js: sole owner, no backup, criticality at or above high. Dependents are deliberately not consulted. |
| Authored versus measured | An authored formula is a product judgement — the pillar weights, for instance — rather than something derived from data. Authored values are labelled wherever they surface. |
| OIS | Organizational Intelligence Score. pillars.orgScore. There is exactly one, per decision D-02. |
| Health delta | The drop in the real organizational health index when a scenario is applied to a mutated copy of the roots bundle. Not a separate simulated-health formula. |
| Cascade reach | What transitively fails downstream when a node fails. Direction matters and was a live bug once — see the decision log. |
| D-nn | A numbered product decision in the central decision log. Not reopened without cause. |
| W-x | A workstream. W-A through W-K are complete; this document is W-L. |
| Frozen roots invariant | One roots read per agent turn, shared by every tool, so no two tools in one answer can disagree. |

End of implementation plan. Companion architecture document: `docs/superpowers/specs/2026-08-27-w-l-agent-interface-design.md`.